## Sheet1
Backlog Item | Sprint Item | Initial estimate of effort
Create UI | Acquire knowledge about XAML | 20
| Design UI | 15
| Create Doc View UI | 10
| Create Doc Delete UI | 3
| Rest (i.e Revision History) when UI is designed | 20
Create Client/Server | Create class diagram | 5
| Create sequence diagram | 3
| Create package diagram | 1
| Handle multiple clients | 3
| Map exact difference between winform and web interface. | 2
| Connection between client and server | 3
| Authentication | 5
Create doc | Create depencies for controller methods | 3
| Document | 2
| Test | 2
Edit doc | Create UI | 1
| Create depencies for controller methods | 3
| Document | 2
| Test | 2
Sync doc | Create UI + diff. view | 10
| Create depencies for controller methods | 4
| Research and develop three-way merge algorithm | 20
Delete doc | Create UI | 2
| Create depencies for controller methods + LINQ | 3
| Document | 2
| Test | 2
Create DB | Domain model | 2
| ER model | 3
| Create .mdx | 5
| DAO + LINQ queries | 7