## Sheet1
Backlog Item | Sprint Item | Initial estimate of effort | Volunteer
Create UI | Acquire knowledge about XAML | 20 | Mikkel
| Design UI | 15 | All
| Create Doc View UI | 10 | Andreas
| Create Doc Delete UI | 3 | Andreas
| Rest (i.e Revision History) when UI is designed | 20 | All
Create Client/Server | Create class diagram | 5 | Mark & Mikkel
| Create sequence diagram | 3 | Christian
| Create package diagram | 1 | Christian
| Map exact difference between winform and web interface. | 2 | Mark
| Connection between client and server | 3 | Andreas
Create doc | Create depencies for controller methods | 3 | Mark
| Document | 2 | Mark
| Test | 2 | Mark
Edit doc | Create UI | 1 | Andreas
| Create depencies for controller methods | 3 | Andreas
| Document | 2 | Andreas
| Test | 2 | Andreas
Sync doc | Create UI + diff. view | 10 | Mikkel
| Create depencies for controller methods | 4 | Mikkel
| Research and develop three-way merge algorithm | 20 | Mark