## Sprint1
Backlog Item | Sprint Item | Volunteer | Initial estimate of effort | 0 | 1 | 2 | 3 | 4 | 5
Create UI | Acquire knowledge about XAML | Mikkel | 20 | 20 | 20 | 14 | 12 | 11 | 11
| Design UI | All | 15 | 15 | 15 | 2 | 2 | 2 | 2
| Create Doc View UI | Andreas | 10 | 10 | 10 | 10 | 9 | 2 | 2
| Create Doc Delete UI | Andreas | 3 | 3 | 3 | 3 | 2 | 1 | 1
| Rest (i.e Revision History) when UI is designed | All | 20 | 20 | 20 | 20 | 20 | 15 | 12
Create Client/Server | Create class diagram | Mark & Mikkel | 5 | 5 | 5 | 5 | 5 | 5 | 5
| Create sequence diagram | Christian | 3 | 3 | 3 | 1 | 1 | 1 | 1
| Create package diagram | Christian | 1 | 1 | 1 | 1 | 1 | 0 | 0
| Map exact difference between winform and web interface. | Mark | 2 | 2 | 2 | 0 | 0 | 0 | 0
| Connection between client and server | Andreas | 3 | 3 | 3 | 3 | 3 | 0 | 0
Create doc | Create depencies for controller methods | Mark | 3 | 3 | 3 | 3 | 3 | 2 | 2
| Document | Mark | 2 | 2 | 2 | 2 | 2 | 2 | 2
| Test | Mark | 2 | 2 | 2 | 2 | 2 | 2 | 2
Edit doc | Create UI | Andreas | 1 | bar: 0 to 5
| Create depencies for controller methods | Andreas | 3 | 3 | 3 | 3 | 3 | 3 | 3
| Document | Andreas | 2 | 2 | 2 | 2 | 2 | 2 | 2
| Test | Andreas | 2 | 2 | 2 | 2 | 2 | 2 | 2
Sync doc | Create UI + diff. view | Mikkel | 10 | 10 | 10 | 10 | 10 | 10 | 10
| Create depencies for controller methods | Mikkel | 4 | 4 | 4 | 4 | 4 | 4 | 4
| Research and develop three-way merge algorithm | Mark | 20 | 20 | 20 | 5 | 0 | 0 | 0
Create DB | Domain model | All | 2 | 2 | 0 | 0 | 0 | 0 | 0
| ER model | All | 3 | 3 | 1 | 1 | 0 | 0 | 0
| Create .mdx | Mark | 5 | 5 | 0 | 0 | 0 | 0 | 0
| DAO + LINQ queries | Mark+Andreas | 7 | 7 | 7 | 7 | 7 | 5 | 4
| Create Entity Framework | Andreas+Mark | 7 | 7 | 7 | 5 | 2 | 0 | 0
|  | Total | 155 | 155 | 146 | 106 | 93 | 70 | 66
Goal for Sprint
|  | Days: | 0 | 0: 5
|  | Estimated effort: | 155 | 0: 0

## Sprint2
Backlog Item | Sprint Item | Volunteer | Initial estimate of effort | 0 | 1 | 2 | 3 | 4 | 5
Create UI | Acquire knowledge about XAML | Mikkel | 11
| Design UI | All | 2
| Create Doc View UI | Andreas | 2
| Create Doc Delete UI | Andreas | 1
| Rest (i.e Revision History) when UI is designed | All | 12
Create Client/Server | Create class diagram | Mark & Mikkel | 5
| Create sequence diagram | Christian | 1
Create doc | Create depencies for controller methods | Mark | 2
| Document | Mark | 2
| Test | Mark | 2
| Create file system | Andreas | 5
Edit doc | Create UI | Andreas | 1
| Create depencies for controller methods | Andreas | 3
| Document | Andreas | 2
| Test | Andreas | 2
| Insert picture | Mikkel | 2
Sync doc | Create UI + diff. view | Mikkel | 10
| Create depencies for controller methods | Mikkel | 4
Create DB | DAO + LINQ queries | Mark+Andreas | 4
Manage docs | Download document from server to client | Mark | 3
| View/Download document revision | Mark | 3