## Sheet1
Backlog Item | Sprint Item | Initial estimate of effort | Volunteer | Day 1 | Day 2 | Day 3 | Day 4 | Day 5
Create UI | Acquire knowledge about XAML | 20 | Mikkel | 20 | 14 | 12 | 11 | 11
| Design UI | 15 | All | 15 | 2 | 2 | 2 | 2
| Create Doc View UI | 10 | Mikkel | 10 | 10 | 9 | 2 | 2
| Create Doc Delete UI | 3 | Mikkel | 3 | 3 | 2 | 1 | 1
| Rest (i.e Revision History) when UI is designed | 20 | All | 20 | 20 | 20 | 15 | 12
Create Client/Server | Create class diagram | 5 | Mark & Mikkel | 5 | 5 | 5 | 5 | 5
| Create sequence diagram | 3 | Christian | 3 | 1 | 1 | 1 | 1
| Create package diagram | 1 | Christian | 1 | 1 | 1 | 0 | 0
| Map exact difference between winform and web interface. | 2 | Mark | 2 | 0 | 0 | 0 | 0
| Connection between client and server | 3 | Andreas | 3 | 3 | 3 | 0 | 0
Create doc | Create depencies for controller methods | 3 | Mark | 3 | 3 | 3 | 2 | 2
| Document | 2 | Mark | 2 | 2 | 2 | 2 | 2
| Test | 2 | Mark | 2 | 2 | 2 | 2 | 2
Edit doc | Create UI | 1 | Andreas | 1 | 1 | 1 | 1 | 1
| Create depencies for controller methods | 3 | Andreas | 3 | 3 | 3 | 3 | 3
| Document | 2 | Andreas | 2 | 2 | 2 | 2 | 2
| Test | 2 | Andreas | 2 | 2 | 2 | 2 | 2
Sync doc | Create UI + diff. view | 10 | Mikkel | 10 | 10 | 10 | 10 | 10
| Create depencies for controller methods | 4 | Mikkel | 4 | 4 | 4 | 4 | 4
| Research and develop three-way merge algorithm | 20 | Mark | 20 | 5 | 0 | 0 | 0
Create DB | Domain model | 2 | All | 0 | 0 | 0 | 0 | 0
| ER model | 3 | All | 1 | 1 | 0 | 0 | 0
| Create .mdx | 5 | Mark | 0 | 0 | 0 | 0 | 0
| DAO + LINQ queries | 7 | Mark+Andreas | 7 | 7 | 7 | 5 | 4
| Create Entity Framework | 7 | Andreas+Mark | 7 | 5 | 2 | 0 | 0